Western Shoshone Project

Update

June 18, 2012

Attention – Phone number correction:

On Thursday June 14, 2012, we mailed out letters to 5291 eligible applicants requesting address and payment verification from the approved eligible applicants. 1087 of those 5291 letters were sent to applicants or their sponsors for those payments designated to be placed in IIM Accounts.

In those 1087 letters we listed an incorrect phone number for Raylene Swan, Fiduciary Trust Officer at the Western Nevada Agency. Please be advised that the correct phone number for Raylene Swan is (775) 887 – 3525.  Raylene may be contacted If you have any questions relating to the applicant’s IIM account.

On May 7, 2012, the Western Shoshone Project Office completed the quality assurance (QA) review process of all 9612 applications that were received by close of business on December 31, 2010.  The Western Shoshone Project Office continues to work with the BIA Central Office to process the appeals that were filed by those applicants that were determined ineligible during the review process.

Target date for the final payment is:  September 30, 2012.  Once all the appeals have been processed and a final judgment roll has been determined on the anticipated date of August 31, 2012, an additional 30 days will be needed to get the correct information transmitted to the Treasury Department for the final payment.  There will be six payment files that will need to be tested and corrected of all errors prior to final transmission to Treasury.  For those individuals that received a partial payment there will be a check file and direct deposit file. For those individuals that did not receive a partial payment but will receive the full payment amount there will be a check file and direct deposit file.  For supervised IIM accounts there will be a file for those individuals that received a partial payment and a file for those individuals that will receive the final full payment amount. We will continue to work diligently on this project to try to get done earlier, however this is the best estimate that we can provide at this time.

How can you help?

- Keep your addresses and telephone contact numbers current.

- Probate: If you have any questions pertaining to the probate process, please contact the Western Nevada Agency Probate Office at (775) – 887 – 3500 or the Eastern Nevada Agency Probate Office at (775) – 738 – 5165).

Please submit any changes of information to:

Western Shoshone Project

Post Office Box 3838

Phoenix, Arizona, 85030

Reminder:  Any change of information must be provided in writing with the applicant’s signature and date of birth included.  Information should be submitted to the above address or faxed to (602) 253-4520.

Any questions should be directed to the Western Shoshone Project Office at (602) 253-0024.  If the line is busy, please try again.